## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team and Freshman Seminar acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions, cross-team testing, and Freshman Seminar testing.
Team Name | term-swen-261-05-g
Testing Team Name | fill in when doing cross-team or Freshman Seminar testing

## Test Plan
User Story | Acceptance Criterion | Sprint 1 | Tester initials; date; comments (required if test failed) | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Player I want to sign-in so that I can play a game of checkers. | Given that I have not yet signed in when I see the Home page then I must see a means to sign-in. (such as a link or button) |  | AW, 9/30
| Given that I am not signed-in when I do click on the sign-in link then I expect to be taken to the Sign-in page, with a means to enter a player name. |  | AW, 9/30
| Given that no one else is using my name when I enter my name containing at least one alphanumeric character and optionally spaces in the sign-in form and click the Sign-in button then I expect the system to reserve my name and navigate back to the Home page. |  | AW, 9/30
| Given that I am on the Sign-in page when I enter a name that does not contain at least one alphanumeric character or contains one or more characters that are not alphanumeric or spaces and click the Sign-in button then I expect the system to reject this name and return the Sign-in page. |  | AW, 9/30
| Given that someone else with my name has signed-in when I enter my name in the Sign-in form and click the Sign-in button then I expect the system to reject my sign-in and return the Sign-in page for me to try a different name. |  | AW, 9/30
| Given that I am signed-in when I navigate to the Home page then I expect to see a list of all other signed-in players. (NOTE: in the next story you will use this list to pick opponents for checkers games.) |  | AW, 9/30
| Given that I am not signed-in when I navigate to the Home page then I expect to see a message of how many players are signed-in but not a list of them (for privacy reasons). |  | AW, 9/30
As a Player I want to start a game so that I can play checkers with an opponent. | Given that I'm signed in when I view the Home page then I can start a game by selecting a player listed on the Home page. |  | HH, 10/4
| Given that the player I selected isn't yet in a game when I select that player then the system will begin a checkers game and assign me as the starting (Red) player and my opponent as the White player. |  | HH, 10/4
| Given that the player I selected is already in a game when I select that player then the system will return me to the Home page with an error message. |  | HH, 10/4. We make the player unclickable.
| Given that I'm waiting for a game when another player selects a game with me then the system will automatically send me to the Game View as the White player. NOTE: the `home.ftl` HTML includes a `<meta>` tag that tells the browser to refresh the game every 5 seconds; thus you need to update the `GetHomeRoute` controller to handle the situation when a player is assigned a game. |  | HH, 10/4
| Given a valid, initial game board when I drag a piece to a white space then the piece should not be droppable. |  | HH, 10/4
| Given a valid, initial game board when I drag a piece to an occupied space then the piece should not be droppable. |  | HH, 10/4
| Given a valid, initial game board when I drag a piece to an open space then the piece should be droppable. NOTE: In this Story the drop action should not do anything; piece movement will be the focus of future stories. |  | HH, 10/4. FAIL, piece moves
| Given a valid, initial game board when I view the board in the browser then my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world. |  | HH, 10/4
As a player I want to be able to resign at any time so that I can end the game. | Given it is my turn when I am in the empty turn state then I must be able to resign. |  |  | Pass | AW; 10/23
| Given it is my turn when I am not in the empty turn state then I must not be able to resign. |  |  | Pass | AW; 10/26
| Given it is not my turn when I click the resign button then I must be able to resign. |  |  | Pass | AW; 10/23
| Given I am in a game when my opponent clicks the resign button then I must be notified they resigned and the game must end. |  |  | Pass | AW; 10/23
| Given I can resign when I resign then I must be sent to the home page. |  |  | Pass | AW; 10/23
As a player I want to be able to move my piece so that I can play webcheckers | Given it is my turn when I drag and drop a piece on a valid black square then the piece should be droppable |  |  | Pass | HH, 10/25
| Given it is my turn when I drag and drop a piece on a white square then the piece should not be droppable |  |  | Pass | HH, 10/25
| Given it is my turn when I drag and drop a piece on a space that is already occupied then the piece should not be droppable |  |  | Pass | HH, 10/25
| Given it is my turn when I drag and drop a piece on a square that is out of my movement range then the piece should not be droppable |  |  | Pass | HH, 10/25
| Given it is not my turn when I try to drag and drop a apiece then I should not be able to click on it |  |  | Pass | HH, 10/25
| Given it is my turn when I move to a valid space then I should be able to backup my move and move again |  |  | Pass | HH, 10/25
| Given it is my turn when I move to a valid space then I should be able to submit my move to end my turn |  |  | Pass | HH, 10/25
| Given It is my turn when I move my piece to the opposite end of the board then my piece should become a king |  |  | Pass | HH, 10/25
| Given it is my turn when I move my king then I should be able to move it north and south |  |  | Pass | HH, 10/25
As a player I want the game to have end conditions so that a winner can be determined | Given it is my turn when I capture all the opposing players piece then the game should be put in the ending state |  |  | Fail | HH, 10/25, When I win the game is stuck in the game window
| Given it is not my turn when all of my pieces are captured then the game should be put in the ending state |  |  | Pass | HH, 10/25
| Given it is my turn when I run out of moves then the game should be put in the ending state |  |  | Pass | HH, 10/25
As a User I want to play a game against an AI so that I don't need an actual opponent to play against. | Given I am in a game with an AI player when I submit a move then I expect the AI to make its move shortly after. |  |  |  |  | Pass | AW 11/10
| Given that I am in a game with an AI player when I win then I expect the game to end and display a message that I won |  |  |  |  | Pass | AW 11/10
| Given that I am in a game with an AI player when the AI wins then I expect the game to end and display a message that the AI won |  |  |  |  | Pass | AW 11/10
As a User I want the AI to pick the move it sees as the best so that I can play a competitive game of checkers. | Given the AI is in a game with another player when it is their turn then they should submit a valid and optimal move. |  |  |  |  | Pass | AW 11/10
As a user I want the AI to make smart moves in reasonable time so I can play a competitive game of checkers | Given the AI is in a game with a player when the user submits their turn then the AI should generate a decision tree of a certain length based on its difficulty class |  |  |  |  | Pass | AW 11/10
| Given the AI is in a game with a player when the user submits their turn then the AI should pick and submit a move within reasonable time (<20 seconds) |  |  |  |  | Pass | AW 11/10
As a player I want to start a game against the AI so that I can play against the computer. | Given I am signed in when I am on the home page then I should be able to start a game against an AI by clicking its name in the online player list. |  |  |  |  | Pass | AW 11/10
| Given I am not signed in when I am on the home page then I should not be able to start a game against an AI. |  |  |  |  | Pass | AW 11/10
| Given I am signed in when I am in a game against an AI then I should not be available to challenge by another player. |  |  |  |  | Pass | AW 11/10
| Given I am signed in when I someone else is in a game with an AI then I should still be able to challenge and start a game with an AI. |  |  |  |  | Pass | AW 11/10
As a user I want to be able to choose to spectate a game so that I can observe checkers games live. | Given I am signed in when I click a users name from the spectate list then I should be able to spectate the selected user. |  |  |  |  | Pass
| Given that I am not signed in when I am on the home page then I should not be able to spectate a user. |  |  |  |  | Pass
| Given I am signed in when I am on the home page then I should be able to see the spectate list. |  |  |  |  | Pass
| Given I am spectating a game when click the exit button then I should be taken back to the homepage. |  |  |  |  | Fail
| Given I am spectating when I can see the gameboard then I should be able to see the total number of spectators. |  |  |  |  | Pass
| Given I am spectating when I can see the gameboard then I should be able to flip the orientation of the gameboard . |  |  |  |  | Fail